## Work-back Schedule
Week | Action | Task
Topic
Program Date
Organizer(s)
Lead
Co-Lead
Team Members
W-15 | Team in Place
Team Lead Selected
Mentor Selected
Team Lead and Mentor Have Flight Plan
Get Conference Call Numbers and Procedures
Team Selected
Contact List in e-format
Meeting Plan Finished
Distribute Meeting Plan and Contact List
W-14 | Vision of Event
Draft Issue Summary
Target List of Speakers and Panelists
Review Schedule With Team
Determine Team Assignments
Decide on Company or Panel Format
Refine Issue Summary For Posting on Web *
W-9 | Qualify Potential Participants
Initial Interviews With a Few Potential Speakers
Refine Focus of Forum
Qualified Pool of Potential Speakers
List of Potential Companies
Qualify Potential Companies
W-9 | Company in Place
Company Identified
Company Confirmed
Obtain Written Info on Company
Convey Guidance on Forum Needs/Format to Company Participant
Refine Issue Summary For Posting Web B *
W-7 | Participants in place
Ranked Speaker List
Moderator Selected
Moderator Confirmed
Panelists Selected
Panelists Confirmed
Bio’s in Hand
Bio’s Distributed *
Participant e-list in Hand
Distribute e-list **
Publicity Requirements to Publicity Chair
Confirm Pre-Prior Month Forum Meeting and Invite
Review Issue Summary, Finalize & Post on Web *
W-6 | Organize & Develop Event
Draft of Meeting Announcement
Review Draft with Publicity Chair
Finalize Meeting Announcement and “e-mailer”
Distribute Announcement
Pre-Prior Month Meeting Agenda
Pre-Prior Month Meeting Parallel to Speaker Prep Mtg
Initiate Conversation With Logistics
Contact Info to Publicity
W-4 | Early Publicity
Verbal Announcement at Prior-Month’s Forum
Handout Distributed at Prior Month’s Forum
Prepare Electronic Release and Web Text *
W-3 | Coordinate Program
Determine if Presenters Will Bring Cards/Literature
Invite Speakers’ Spouses/Significant Others As Our Guests, Determine Dietary Needs.
Co-ord with Logistics on Any Special Needs
Moderator Bio to MITEFNW Chair
Other Participant Bios to Moderator
Work with Publicity Chair to Prepare 2nd e-mailer
W-3 | Prep Presenters
Dress Rehearsal of All Participants
Reinforce That This Is Not A Sales Pitch Opprnty
Make Sure Company Presentation Frames the Issue and Sets Stage for Discussion
Prepare a speaker briefing for day-of
W-2 | Publicity
Verify Second e-mail Is Sent
Check Attendance
Determine If Additional Publicity Is Needed
W-1 | Final Nits
Additional Publicity If Needed
Hold Prep Meeting with Moderator and Panelists by Phone or In Person
Insure That Alliance Strategies Has All Names (Including Guests)
Last Minute Adjustments to Panelist and Program Needs to Alliance Strategies
Coordinate Last Minute Moderator’s and Panelists’ Needs with Logistics Committee
Prepare a Run-of-Show sheet
W=0 | The Program!
Agenda
W+1 | Post-Program
Send Thank-you Letters
Debrief Presenting Company
Participate at the Program Committee Meeting The Week After The Event
Send Survey
Last edit: | 2023-07-02
Jimmy Jia
This work is licensed under a Creative Commons Attribution 4.0 International License

## Team Contact Info
| Phone | Email
Organizer(s)
Lead
Co-Lead
Team Members